## Sheet1
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6
Yunyi | Defined the core score-reading functionality and participated in backend architecture planning with Angxiao Xu. Clarified how score data would be processed and integrated into the system. | Worked on backend development with Angxiao Xu, focusing on implementing and structuring the score-reading logic and preparing interfaces for later frontend connection. | Integrated code from different functional modules, organizing score extraction, prediction outputs, and system logic into a unified backend structure. | Independently designed and implemented the frontend UI/UX, focusing on user interaction flow and score visualization. | Independently connected the frontend and backend, handling data communication, debugging request–response logic, and ensuring smooth system interaction. | Conducted final integration and testing, fixed bugs related to score loading and UI responses, and prepared the system for final submission.
Angxiao | Worked closely with Yunyi on defining the core score-reading functionality and clarifying the system’s technical direction. Contributed to early discussions on how score data would be parsed and prepared for later integration. | Collaborated with Yunyi on backend development, focusing on implementing score-processing logic. Helped structure the backend workflow to ensure extracted data could be passed to later modules. | Continued joint backend work with Yunyi, integrating functional components and refining the system structure. Assisted in organizing score extraction outputs to ensure backend compatibility. | Identified and finalised the required models and core programs. Began consolidating developed components, aligning model outputs with system logic. | Completed backend integration, ensuring modules worked as a coherent system. Conducted testing, identified bugs, and refined logic to improve stability. | Participated in final integration and testing with Yunyi. Focused on debugging issues related to score loading, system responses, and final submission.
Julia | Website idea and create group document | Website idea and create group document | Searching for workable datasets | Making the recommendation algorithm | Finalising the recommendation algorithm | Trying to connect front end and backend
Silas | Created group document with subject and group members | Handed in the group document; Tried working with omnizart | Searching for workable datasets | Created a small dataset in VScode; Tried working with the dataset to connect it with Google Colab | Tried connecting backend and frontend | Tried connecting backend and frontend; Created presentation slides